## Sheet1
Required Hardware
]
Last Edit: Sep-24-17
Dicussion Topics
1000 Net Production update:
Sunny - Sep-20-17 | We have sewn about 700 interior nets.We are just waiting for the bags and bars to package it. Regarding bag and bars,It will be complete by the end of Sep. as plan.
Ben - Sep-22-17 | OK Good
1200 Bar Kits
Sunny - Sep-20-17 | Pls note your order is 1200 bars,not 1000 bars.It will be complete by the end of Sep. But we have not started to making the straps.It may need 15 days to finish it.
Ben - Sep-22-17 | Ok good, please activate the straps asap. . with thicker webbing if your factory has thicker webbing, we are ok for price increase.
1000 Bars (for Nets)
Ben - Sep-24-17 | Please confirm you have everything for the bar’s that go with the 1000 Int nets.
Carabiners for 1200 Bar kits
Sunny Sep-20-17 | Pls note your order is 1200 bars,not 1000 bars.It will be complete by the end of Sep. But we have not started to making the straps.It may need 15 days to finish it.
Ben Sep-20-17 | Why have you not order it from Tomy. Please order asap.. we need you to plan and book your own carabiners, and then send us your PI and we will pay 30% then remainder when you get them.
Carabiners for 1200 Bar kits
HeadRest Straps
Next month we will order large volume order with Tomy by asking u to place order and again we would pay through u and have a large stock for you for 2 future order.
Sunny Sep-21-17 | Reply: We talked about it before.If we buy the carabiner for bar.It will not be USD0.82/pc.We need you to supply us the carabiners.So we didn't order it from Tony for the bars.If you need us to buy it. The carabiner will be USD1/pc for bars.It's not economic.If you buy it.I think It should be cheaper.
Ben - Sep-21-17 | Why? This does not make any sense to me. Why does Tony need to know what ur doing with the carainbers?? Are you not hitting the 5k moq order when wanting to order for the bars?? Please place 5000 unit order with him and should not change from .82 Need to sove this asap.
Sunny Sep-21-17 | Reply:Pls kindly note the cost of carabiner rose a lot.We need to offer you at USD0.88 each carabiner for int.bars in your next orders .Pls kindly confirm it. If we buy it.We need to order 5000 pcs at least.With USD1/pc.Pls kindly give us your comment.Thanks.
Ben - Sep-21-17 | Please see my comments above.. I don’t understand why its $1 per when buying for the bar kits.. tell them its for nets???
Sunny Sep-21-17 | Reply:Pls note Tony doesn't care about for net or bars.We need to offer you at USD0.95 each carabiner for bars.If you can supply us the carabiners.That will be better.
Ben - Sep-24-17 | Ok am I correct to understand that your having to increase the price to us for the carabiners (when your adding them to our Bar kits) because you make less margins on the bar kits then you do on the nets ?
and your able to absorb the carabiner cost into the cargo nets cost easier so you offer then to us cheaper when we buy the nets with it?
Sunny Sep-22-17 | Tomorrow morning,I will contact Tony.Then I will reply you email about carabiners.Pls note. I'm sure we are not able to offer you USD0.82/pc for your next orders.As Tony said their cost increased a lot.And US dollar devaluled a lot.
I think that is the real reason why Kevin stop production.I rembemed his price is only USD0.75/pc.That is under his cost.
Ben - Sep-24-17 | I understand Sunny.
HeadRest Straps - Webbing
Sunny Sep-21-17 | In order GNS-0417--1000 interior nets and 1200 bars,We will make the straps as before just with thicker webbing.Is that right?Pls kindly confirm it again.Thanks.
Ben - Sep-21-17 | Yes that is Correct Sunny. Same style strap (we can call them Original Straps) except with thicker webbing
HeadRest Straps - Paper Tags
Sunny - Sep-20-17 | Could you pls kindly advise whether the new strap need the paper label or not? As I found you put on a pvc label on the new strap.You may need not the paper label any more for the new straps. Thanks.
Ben - Sep-24-17 | Yes Sunny we do need the paper style ‘warning labels’ for even the new headrest straps.
Delivery Plan
Sunny - Sep-19-17 | Could you pls kindly advise how you want us to ship GNS-0417 to you? Ship 500 int. net in Oct.Another 500 int.net in Nov.?
Ben - Sep-24-17 | Sunny we would take 500 As soon as possible. And then the remainder 500 as soon as possible too.. What is possible?
Order Number: GNS-0417 Order Date Placed: Aug-10-17 Quantity : 1000 Int Nets, 1200 Bar kit
Hardware Quantity Needed: Carabiners _____ C-rings ______ D-Rings _____ FS Buckel _____
Required Deliver Date by Ben: ____________ Projected delivery Date by Sunny: ___________ Actual Delivery Date: ___________